## Sheet1
Toolset | Tool/functionality | Issue | Reported by | Reported | Corrected | Status | Feedback from authors
General | Tag for Timber columns | Colour of tag is incorrect (should be brown instead of purple) | J Du Bois | 2025-09-23 | 2025-09-29 | Completed
General | Tags for plates | Standard font size is too large (some are 12 instead of 10) | J Du Bois | 2025-09-23 | 2025-09-29 | Completed
General | Cloud+ | Line width of text outline to be set = 1,0 to match other callouts and textboxes | J Du Bois | 2025-09-23 | 2025-09-29 | Completed
Formwork foundations | Pile legend | Text scaling goes awry @ larger scales (e.g. 1:250) | J Du Bois | 2025-09-23 | 2025-09-29 | Completed
Formwork details and sections | Silicate, masonry, timber | Border 1,00 → 0,00 like other elements | M Vervaet | 2025-09-23 | 2025-09-29 | Completed
Formwork details and sections | Isolation | is missing | M Vervaet | 2025-09-23 | 2025-10-03 | Completed
Loading | (general) | Not on scale → on scale 1/50 | M Vervaet | 2025-09-23 | 2025-09-23 | Completed | standard text size adjusted to 6 (less obtrusive)
Formwork foundations | Custom pilecap | No sketch-to-scale, not usefull for foundation soles (funderingszolen) → sketch-to-scale | M Vervaet | 2025-09-23 |  | Void | Not changed: SSD Foundationton tools are created as snapshots to allow them to be counted by number of foundations instead of area of foundations.
General | Openings | 80% is too hard → 40% is better | M Vervaet | 2025-09-23 | 2025-11-06 | Completed
General Bluebeam | Pen | "pen" is usefull during meetings to quick draw or clarify | M Vervaet | 2025-09-23 |  | Void | Not added. Use shortut [P]
General | (missing) | some tools for quick drawing, without using "structural elements", but with respect for layers | M Vervaet | 2025-09-23 |  | Void | Not added. SSD toolchest contains sufficient tools
Formwork general | Generic concrete column | mode "properties" ↔ "drawing" | M Vervaet | 2025-09-23 | 2025-10-03 | Completed
General | General notes legend | Size of legend to be reduced. If resized after placement the text scaling goes awry | J Du Bois | 2025-10-03 | 2025-11-06 | Completed
General | General notes legend | Split up external and internal notes + move text about thickness to internal part | M Vervaet | 2025-10-09 | 2025-11-24 | Completed
Loading | area loading on plate | "on slab" (not plate) | M Vervaet | 2025-10-09 | 2025-11-12 | Completed
Loading | area loading on plate | remove self weight, only useful for light structures | M Vervaet | 2025-10-09 |  | Void | Remains. Useful for load takedown. Also see general notes
Formwork foundations | Piles | in list with markups, the color of all piles is "red", because the border (of 0 pt) is red, color of the piles is better? = double check when changing pile types | M Vervaet | 2025-10-09 | 2025-11-06 | Completed
Reinforcement 1:50 | (missing) | predalwapening → same as slab thickness, but with fixed arrow? | P Vanderhaeghe | 2025-10-21 | 2025-11-24 | Completed
Reinforcement 1:50 | (missing) | text label for green reinforcement | P Vanderhaeghe | 2025-10-21 | 2025-11-06 | Completed
General | Comments | which remark used for text on drawing by VN? Rose? | P Vanderhaeghe | 2025-10-21 | 2025-11-06 | Void | Internal remarks, including remarks to Vietnam = pink
General | element thickness | cm and mm → confusing? | P Vanderhaeghe | 2025-10-21 |  | Void | Please see general notes for clarification
Formwork details and sections | Existing concrete | dark grey, is missing | P Vanderhaeghe | 2025-10-21 | 2025-11-06 | Completed
General | Measurement | "free text" (e.g. for starter bars: no need for exact drawing) | P Vanderhaeghe | 2025-10-21 | 2025-11-06 | Completed
Formwork general | Steel columns above | in layer "column" → "upper structure" | M Vervaet | 2025-10-22 | 2025-11-06 | Completed
Loading | all loads | add possibility to add leader (useful for walls with zones with different loads) | M Vervaet | 2025-10-22 | 2025-11-06 | Completed
General | (missing) | Slab border | M Vervaet | 2025-10-22 | 2025-11-12 | Completed
General Bluebeam | Legend | If the tool does NOT have Line width = 0,00, then the legend does not work if drawing scale does not equal toolchest scale. | J Du Bois | 2025-10-28 |  | Void | However it works fine on Maarten's Revu
General | North symbol | North symbol added | J Du Bois | 2025-11-06 | 2025-11-06 | Completed
Reinforcement 1:50 | (missing) | stirrups + length of the zone | M Vervaet | 2025-11-24 | 2025-11-24 | Completed
General Bluebeam | rectangle-on-scale | has error in label + layout as opening → reset both | M Vervaet | 2025-11-24 | 2025-11-26 | Completed
General | level on plan | tool size adjusted and text added | J Du Bois | 2025-11-26 | 2025-11-26 | Completed
General | measurement tools | start- and end ticks modified to be less obtrusive & more scalable | J Du Bois | 2025-11-26 | 2025-11-26 | Completed
General Bluebeam | graphics | Difficult to describe in words, but sometimes coloured lines and areas in all colours of the rainbow appear across the screen when editing markups. | A Maes | 2025-11-07 |  | Void | See tips & tricks on DDG0010
General Bluebeam | general | I cannot use two different measurement scales on one page. For example, a detail on a floor plan. | A Maes | 2025-11-07 | 2025-11-26 | Completed | See tips & tricks on DDG0010: Viewports
General Bluebeam | screen area | The default layout of BlueBeam has a double bar at the bottom and top, which takes up a lot of screen real estate. | A Maes | 2025-11-07 | 2025-11-26 | Completed | Status bar removed to give more usable screen area
General Bluebeam | zoom | To zoom in and out, you cannot simply move your mouse to the window and press Ctrl + scroll. You must first click in the window. This is inconvenient if you are working in multiple windows simultaneously. | A Maes | 2025-11-07 |  | Void | See tips & tricks on DDG0010: Single page vs Continuous mode
General Bluebeam | file size | With larger files, everything works noticeably slower than with PDF Xchange. | A Maes | 2025-11-07 | 2025-11-26 | Completed | We are working with a lot more 'intelligent' data than in PDF exchange. To reduce file size go to: Document > Reduce file size
General Bluebeam | general | For files with markups created in PDF Xchange, the properties of the markups (text colour, margins of text in text boxes) change when you drag them or edit the text. | A Maes | 2025-11-07 |  | Void | Possibly a compatibility issue between PDF Exchange and Revu, but in the long term we should not have much to do with PDF Exchange.
General Bluebeam | general | The snapping angles for drawing lines are 45° instead of 15°. | A Maes | 2025-11-07 |  | Void | True, but you can add an angle measurement and then draw a line by following the measurement.
General Bluebeam | general | Copy and paste: best to use control + shift + v to end up in the same place. It's not a big deal, but it's a bit less convenient when copying and pasting a lot. | A Maes | 2025-11-07 |  | Void | See tips & tricks on DDG0010
General | measurement tools | Measurement units always default to mm | A Maes | 2025-11-10 |  | Void | Go to Revu > Preferences > Tools > Markup: Ensure that all tickboxes are activated except Show author and date in pop-ups. Always use the SSD measurement tools, not the default ones
Loading | loading notation | Spelling errors. Dutch to be changed to English. Grammar error. | J. Ver Elst | 2025-11-17 | 2025-11-26 | Completed
Formwork details and sections | section 'blocks' | 1pt edge white edge only on some of the 'blocks' | J. Ver Elst | 2025-11-17 | 2025-11-26 | Completed | Edge removed (changed to 0pt thickness)
Reinforcement 1:50 | reinforcement tags | Size of reinforcement tags and black circle looks disproportionate | J. Ver Elst | 2025-11-17 |  | Void | Please set scale of drawing before inserting tools and don't use 1:25 tools on 1:50 drawing (text scaling goes awry)
Reinforcement 1:50 | reinforcement tags | What is the white textbox area for below the text? Can it be removed? | J. Ver Elst | 2025-11-17 |  | Void | No. You can use ctrl + Z to autosize textbox fields but sometimes there is a minimum limit.